## Slide 1: D.Eco Application
Presented by Code Monkey

## Slide 2: System Inception
Use Case Model
Risk Analysis
Technology Plan
Effort Estimate
System Architecture
Code Monkey
April 5, 2017

## Slide 3: Use Case Model
Code Monkey
April 5, 2017

## Slide 4: Technology Plan
Technology | Experience Rating
Phone App Technologies | 
IOS | Tutorial
Android | None
Cordova | Tutorial
Windows 10 Phone | None
Map Technologies | 
Google Maps | Tutorial
Microsoft Bing Maps | None
Open Layers | None
OpenStreetMap | None
Code Monkey
April 5, 2017

## Slide 5: Technology Plan
 | Experience Rating
Application & Web Development | 
Java | Small Scale
Swift | Tutorial
HTML 5 | Small Scale
Javascript | Tutorial
JQuery Mobile | Tutorial
Bootstrap Framework | Tutorial
Iconic Framework | None
Web Server Scripting | 
PHP | Small Scale
Microsoft ASP.NET | None
Code Monkey
April 5, 2017

## Slide 6: Risk Analysis
Risk | Mitigation
No experience with IOS development | Schedule time and work through tutorials
Limited experience with app development | Schedule time and work through tutorials
Limited experience with tools (Cordova, Git, and Visual Paradigm) | Schedule time to learn about the tools and work through the tutorials
Team member conflicting schedules | Plan meetings far in advance and communication in dividing work
No experience accessing GPS in mobile | Schedule time to learn and work through tutorials
Limited information on expected product | Walkthroughs with end users
Limited time to finish product | Manage time efficiently
Code Monkey
April 5, 2017

## Slide 7: Effort Estimate
Screen/Report | Complexity | Object Points | Notes
View Campus | 1 | 1 | Screen will be constructed by reading Drury location from the data source.
Access Menu | 1 | 1 | Simple drop down with text tabs.
Code Monkey
April 5, 2017

## Slide 8: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
Take 21 Tree Tour | 2 | 2 | Screen will be constructed by Drury's location and individual location from the data source.
Subscreen |  |  | 
Read About Trees | 1 | 1 | Simple text with some images on screen.
Search Tree Species | 1 | 1 | Simple search bar that accesses data source.
View Specific Trees on Campus | 2 | 2 | Filter specified tree request from search bar, and access data source.
Code Monkey
April 5, 2017

## Slide 9: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
Take Building Tour | 2 | 2 | Screen will be constructed by Drury's location and individual location from data source.
Subscreen |  |  | 
Read About Repurposed Pieces | 1 | 1 | Simple text with some images on screen.
Code Monkey
April 5, 2017

## Slide 10: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
Take Grass Tour | 2 | 2 | Screen Will be constructed by Drury's location and individual location from data source with grass location.
Subscreen |  |  | 
Read About Grasses | 1 | 1 | Simple text with some images on screen.
Code Monkey
April 5, 2017

## Slide 11: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
Take Repurposed Pieces Tour | 2 | 2 | Screen will be constructed by Drury's location and individual location from data source with repurposed pieces location.
Subscreen |  |  | 
Read About Repurposed Pieces | 1 | 1 | Simple text with some images on the screen.
Code Monkey
April 5, 2017

## Slide 12: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
Manage Repurposed Pieces | 1 | 1 | Simple screen and access to the database.
Manage Grass | 1 | 1 | Simple screen and access to the database.
Manage Trees | 1 | 1 | Simple screen and access to the database.
Screen Total |  | 20 | Total object points for screen.
Code Monkey
April 5, 2017

## Slide 13: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
3GL Modules |  |  | 
Map Modules | 5@10 | 50 | Module requiring scripting against a map API.
GPS Tour | 5@10 | 50 | Module to find individual location with GPS.
Server Modules | 4@10 | 40 | Data server for all 4 Map Modules.
3GL Total |  | 140 | Total object points for 3GL Module.
Total Object Points |  | 160 | Total object points for the project.
Code Monkey
April 5, 2017

## Slide 14: Effort Estimate
Productivity (PROD)
  PROD estimate is normal (10)
  PROD = 160 NOP / 16 person months
  PM = 4hr x 1 week x 4 weeks
  Justification: students
Some code reuse is anticipated so adjusted effort = NOP
  NOP = (160 Obj pts x (100-0.1)) / 100 = 159.8
Effort Estimate in person months (PM) (PM = 16)
  Effort(PM) = 159/10 = 15.9 person months
Code Monkey
April 5, 2017

## Slide 15: Initial Architecture
Code Monkey
April 5, 2017

## Slide 16: Security Risk
Penetration attacks
  Denial of service
Man in the middle attack
SQL injection
Penetration attacks
Code Monkey
April 5, 2017

## Slide 17: Plan – Sprint 1
What | Who | When
Requirements (Update Use Case) | Bijan | April 7, 2017
Analysis (Update cost, risk & effort estimate) | Kylie, Cyler, Cory | April 21, 2017
Design (Platforms & Architecture) | Fisal, Morgan | April 21, 2017
Code Monkey
April 5, 2017